## Gantt Chart
GANTT CHART | [49 empty] | https://goo.gl/4UV8Cz
PROJECT TITLE |  | Understanding Success in Local Business Mobile & Web Apps | [5 empty] | COMPANY NAME | [8 empty] | CRAVER SOLUTIONS
PROJECT MANAGER |  | Michael Jones | [5 empty] | DATE | [8 empty] | April 23, 2024 - June 25, 2024
| TASK | SUBTASK | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9
[5 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| Project Conception and Initiation | Project Kickoff Meeting | All | 100% | bar: WEEK 1 M; WEEK 9 T
|  | Develop Project Plan and Objectives |  | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 9 T
|  | Proposal for MDS - Draft |  | 85% | bar: WEEK 1 TH to WEEK 2 M; WEEK 9 T
|  | Proposal Approval by Craver |  | 100% | bar: WEEK 2 W to WEEK 2 TH; WEEK 9 T
|  | Proposal for MDS - Final |  | 50% | bar: WEEK 2 TH to WEEK 3 M; WEEK 9 T
| Data Preparation | EDA | All | 30% | bar: WEEK 2 F to WEEK 3 W; WEEK 9 T
| Conducting Analyses | Key Objective 1 | Natalie / Jade | 0% | bar: WEEK 3 TH to WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 9 T
|  | Key Objective 2 | Christopher | 0% | bar: WEEK 3 TH to WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 9 T
|  | Key Objective 3 | Jacob | 0% | bar: WEEK 3 TH to WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 9 T
|  | Key Objective 4 | Pranav | 0% | bar: WEEK 3 TH to WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 9 T
|  | Key Objective 5 | Jade | 0% | bar: WEEK 3 TH to WEEK 4 F; WEEK 5 T to WEEK 5 F; WEEK 9 T
| Deliverables Preparation | Dashboard Development | All | 0% | bar: WEEK 6 M to WEEK 7 F; WEEK 9 T
|  | Final Report |  | 0% | bar: WEEK 7 TH to WEEK 8 F; WEEK 9 T
| Presentation | Prepare Midterm / Final Slide Deck | All | 0% | bar: WEEK 4 F to WEEK 5 T; WEEK 8 W to WEEK 9 T
|  | Presentation Midterm / Final |  | 0% | bar: WEEK 9 T
| TASK | SUBTASK | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 M: WEEK 1; WEEK 2 M: WEEK 2; WEEK 3 M: WEEK 3; WEEK 4 M: WEEK 4
[5 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| Project Conception and Initiation | Project Kickoff Meeting | All | 100% | bar: WEEK 1 M
|  | Develop Project Plan and Objectives |  | 100% | bar: WEEK 1 T to WEEK 1 F
|  | Proposal for MDS - Draft |  | 85% | bar: WEEK 1 TH to WEEK 2 M
|  | Proposal Approval by Craver |  | 0% | bar: WEEK 2 W to WEEK 2 TH
|  | Proposal for MDS - Final |  | 50% | bar: WEEK 2 TH to WEEK 3 M
| Data Preparation | EDA | All | 30% | bar: WEEK 2 F to WEEK 3 W
| Conducting Analyses | Key Objective 1 | Natalie / Jade | 0% | bar: WEEK 3 TH to WEEK 4 F
|  | Key Objective 2 | Christopher | 0% | bar: WEEK 3 TH to WEEK 4 F
|  | Key Objective 3 | Jacob | 0% | bar: WEEK 3 TH to WEEK 4 F
|  | Key Objective 4 | Pranav | 0% | bar: WEEK 3 TH to WEEK 4 F
|  | Key Objective 5 | Jade | 0% | bar: WEEK 3 TH to WEEK 4 F
| Deliverables Preparation | Dashboard Development | All | 0%
|  | Final Report |  | 0%
| Presentation | Prepare Midterm / Final Slide Deck | All | 0% | bar: WEEK 4 F
|  | Presentation Midterm / Final |  | 0%
| TASK | SUBTASK | TASK OWNER | PCT OF TASK COMPLETE | WEEK 1 M: WEEK 5; WEEK 2 M: WEEK 6; WEEK 3 M: WEEK 7; WEEK 4 M: WEEK 8 | WEEK 9
[5 empty] | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F | M | T | W | TH | F
| Project Conception and Initiation | Project Kickoff Meeting | All | 100%
|  | Develop Project Plan and Objectives |  | 100%
|  | Proposal for MDS - Draft |  | 85%
|  | Proposal Approval by Craver |  | 0%
|  | Proposal for MDS - Final |  | 50%
| Data Preparation | EDA | All | 30%
| Conducting Analyses | Key Objective 1 | Natalie / Jade | 0% | bar: WEEK 5 W to WEEK 5 F
|  | Key Objective 2 | Christopher | 0% | bar: WEEK 5 W to WEEK 5 F
|  | Key Objective 3 | Jacob | 0% | bar: WEEK 5 W to WEEK 5 F
|  | Key Objective 4 | Pranav | 0% | bar: WEEK 5 W to WEEK 5 F
|  | Key Objective 5 | Jade | 0% | bar: WEEK 5 W to WEEK 5 F
| Deliverables Preparation | Dashboard Development | All | 0% | bar: WEEK 6 M to WEEK 7 F
|  | Final Report |  | 0% | bar: WEEK 7 TH to WEEK 8 F
| Presentation | Prepare Midterm / Final Slide Deck | All | 0% | bar: WEEK 5 M; WEEK 8 W to WEEK 9 M
|  | Presentation Midterm / Final |  | 0% | bar: WEEK 5 T